Solo Service Group Contract Mobilisation Meeting

13th October 2022

| 1. | Introductions and apologies |  |  |
| --- | --- | --- | --- |
|  | Present: GCC –Cathy King (CK), John Stephens (JS), Angela Carter (AJC), Kim Ford (KLF), Solo Service Group - Paul Drakeley (PD), Dave Hutin (DH), Shan Balakrishan (SB), Muhammad Umer (MU), Mike White (MW) Apologies: Julie Webber (JEW), Clive Roberts (CR) |  |  |

| 2. | Actions from previous meeting | Action | Completion Date |
| --- | --- | --- | --- |
|  | JS to chase Glen Cleaning for TUPE information. TUPE information received but it was incorrect. This has now been rectified | JS | Completed |
|  | CR to send draft introductory email to GCC To be emailed to GCC today | CR |  |
|  | AJC to send Solo updated list of schools that have signed up to new contract | AJC | Completed |
|  | Woodmancote - School remeasured, and variation issued. CR to confirm new hours | CR | Completed |
|  | Glenfall School remeasured. JS to send variation. CR to confirm new hours | JS CR | Completed |
|  | Mitton Manor - CR to confirm penalty costs with KLF | CR | Completed |
|  | St James - PD to visit school and speak to Hazel Martindale, the Business Manager MU visited and reassured school. Supervisor vacancy advertised | PD | Completed |
|  | PD to contact Lynn Davies, Operations Manager for SANDmat. PD has left Lynn a voicemail and will now email | PD |  |
|  | CR to send GCC vendor information asap. | CR | Completed |
|  | CR to send GCC an example format of invoice and backing sheet | CR | Completed |
|  | JS to work out totals for October 2022 | JS | Completed |
|  | GCC to share contract guide with Solo | JS |  |
|  | Oakwood School are looking to bring part of the school onto contract. The rest will remain in house until cleaner leaves. JS to send CR bill of quantity to price | JS | Completed |
|  | Prices required for 5 sites: GHAC, Occupational Health, Social Work Academy, Forest Record Store and 48 London Road | CR | Completed |
|  | The signed Contract is with GCC’s solicitor. CK to chase This has been chased but has not yet been received | CK |  |
| 3. | Health and Safety |  |  |
|  | No accidents or near misses |  |  |
| 4. | Mobilisation Plan |  |  |
|  | Site visits All sites have now been visited. Recruitment Chris Palmer, Solo contract manager in Gloucester will take on the Forest of Dean. PD to send GCC list of sites and area managers PD to send GCC Chris Palmer’s contact details Some site vacancies have been filled and interviews planned for others. There will be a big push next week to try and fill vacancies for the start of the contract. St James - interviews next week for supervisor Belmont – interviews next week for cleaner Leckhampton – advertising for 2 cleaners Bamfurlong depot – no interest in position yet Andoversford - Interviewing Newnham – 2 cleaners have decided not to TUPE to Solo. PD to contact them to see if he can persuade them as school are happy with them. River CC – Cleaner from the police station to take this position Lydney Library - vacancy Dinglewell Infants – SB taking over site Upton St Leonards – 2 vacancies filled | PD PD |  |
| 5. | Quality and Service delivery |  |  |
|  | Dinglewell Infant October deep clean Need to book the deep clean with school to check when the school is open Cover cleaning is an issue here due to the limited cleaning window given as the caretaker locks up at 6pm. Forest Records Store dates of cleaning Only twice a month on a Tuesday and cleaning is 6 times a year. AJC to email dates for cleaning which is next due in December. Original plan was for the cleaner at GIS Mitcheldean, which is next door, to take it on Oakwood Primary School School is now looking to bring another part of the school onto contract. JS to send revised bill of quantity for pricing | AJC JS |  |
| 6. | Finance |  |  |
|  | Sample invoice has been sent to KR, GCC |  |  |
| 7. | Management information |  |  |
|  | Nothing to report |  |  |
| 9. | Personnel |  |  |
|  | Solo has meetings arranged with mobile staff to see if they are transferring. Solo has resources they can use if mobile staff choose not to TUPE over. |  |  |
| 10. | DBS and Safeguarding |  |  |
|  | Safer Recruitment Policy GCC will email a letter to schools for their single central record to confirm Solo comply with recruitment and safeguarding legislation. Solo to email GCC up to date safer recruitment policy, safeguarding policy and DBS policy. Safeguarding training All staff must complete safeguarding training. Some schools will get the cleaners to attend school safeguarding training and the hours come out of their cleaning time. As a minimum all staff need to receive safeguarding training at induction and sign a form to confirm. They also need to be aware of the individual school’s safeguarding policy and who the designated safeguarding officer is. Solo to send AJC safeguarding training in place GCC safeguarding training to be arranged for Solo Managers by CK Monthly DBS update needs to confirm date of safeguarding training | CR/PD CR/PD CK |  |
| 11. | Equipment and facilities |  |  |
|  | Pattersons are delivering equipment to sites next week. Shire Hall equipment is being delivered on Wednesday 19th October. SB has arranged storage Scrubber dryers to be ordered in a few weeks’ time. Training to be arranged on new equipment |  |  |
| 12. | Marketing |  |  |
|  | Nothing to report |  |  |
| 13. | Any Other Business |  |  |
|  | Longborough have now requested to join the contract. School was tendered for so TUPE applies. MW to visit school today | MW |  |
|  | Access to schools during half term has been arranged |  |  |
|  | Libraries – all libraries should be cleaned on the days they are open which includes Saturdays. This is not happening on all sites and needs to be rectified. AJC to send up to date library opening times to Solo | AJC |  |
|  | Woodmancote Solo have concerns about the change in measurements for Woodmancote. This will mean a reduction of 20 hours per week. Solo do not think this is achievable. JS to send Solo site plan Meeting to be arranged with school to discuss hours | JS PD/ MU |  |
|  | GCC no longer require Covid cleans on corporate sites |  |  |
|  | Date of next meeting Catch up - 20th October at 2pm - Microsoft Teams Contract Progress Meeting - 15th November at 2pm – Coombe Room, Shire Hall |  |  |